## TASKS
Planning and Schedule
MY TASKS | START DATE | DUE DATE | % COMPLETE | DONE | NOTES
Phase 1 |  |  |  | 0
Project selection and team formation | 2024-09-06 | n/a | 100% | 1
Group Meeting | 2024-09-08 | n/a | 100% | 1
Group Meeting with Professor WeiPing Zhu | 2024-09-10 | n/a | 100% | 1
Group meeting | 2024-09-11 | n/a | 100% | 1
Proposal Completed | 2024-09-15 | 2024-09-19 | 100% | 1
Project Approval by Supervisor | 2024-09-16 | n/a | 100% | 1
Group meeting | 2024-09-29 | n/a | 100% | 1
Meeting with Space Concordia | 2024-10-01 | n/a | 66% | 0
Group meeting | 2024-10-05 | n/a | 100% | 1
Phase 1 Report Submitted | 2024-09-28 | 2024-10-05 | 100% | 1
Phase 1 presentation | 2024-10-05 | 2024-10-07 |  | 0
0
Phase 2 |  |  |  | 0
All group meeting plan |  |  |  | 0
Final Design Approval |  |  |  | 0
Software Acquisition |  |  |  | 0
Hardware Acquisition |  |  |  | 0
Phase 2 Report Submission |  |  |  | 0
Phase 2 Presentation |  |  |  | 0
0
Phase 3 |  |  |  | 0
All group meeting plan |  |  |  | 0
Begin Prototype Implementation |  |  |  | 0
Testing and Troubleshooting of Prototype |  |  |  | 0
Phase 3 In lab-demo |  |  |  | 0
0
Phase 4 (Final Product) |  |  |  | 0
All group meeting plan |  |  |  | 0
Final design implementation |  |  |  | 0
Verification and testing |  |  |  | 0
Phase 4 In-Lab Demo |  |  |  | 0
Phase 4 Report Submission |  |  |  | 0
Phase 4 Final Poster Presentation |  |  |  | 0
0
0
0
0
0
0
0
ALL TBD
Phase 2 report and presentation will be held on end of November to beginning of December
ALL TBD from January to February in 2025
ALL TBD from March to April in 2025